## Sheet1
✦ Product Backlog for Bagani App
ID | User Story | Priority | Estimate (Story Points) | Status | Acceptance Criteria
1 | As a user, I want to browse available plants for sale, so I can find the plant I want to buy. | High | 8 | To Do | - Users can filter and search plants based on type, price, and location. - Plant listings display clear images and detailed descriptions.
2 | As a user, I want to list plants for sale, so I can sell plants to other users. | High | 8 | To Do | - Users can add new Plant listings with images, descriptions, and prices. - Users can manage their listings and see all active posts.
3 | As a user, I want to exchange plants with other users, so I can acquire new plants. | High | 8 | To Do | - Users can propose Plant exchanges with other users. - Users can accept or decline exchange proposals.
4 | As a user, I want to communicate with other users, so I can discuss details of buying, selling, or exchanging. | Medium | 5 | To Do | - Users can message each other through the app. - Notifications are sent when a message is received.
5 | As a user, I want to view my transaction history, so I can keep track of my sales and exchanges. | Medium | 3 | To Do | - Users can see a list of completed sales and exchanges. - Transaction history includes dates and details of each transaction.
6 | As a user, I want to rate and review other users, so I can build trust in the community. | Medium | 5 | To Do | - Users can leave ratings and reviews after a transaction. - Average ratings are displayed on user profiles.
7 | As a user, I want to receive notifications, so I can stay updated on my transactions. | High | 3 | To Do | - Users receive Notifications for messages, offers, and status updates. - Users can enable or disable Notifications in their settings.
8 | As a user, I want to update my profile, so I can keep my contact and personal information accurate. | Medium | 3 | To Do | - Users can edit their profile information including name, email, and location. - profile updates are reflected immediately on the platform.
9 | As a user, I want to save favorite plants, so I can easily return to them later. | Medium | 3 | To Do | - Users can mark plants as favorites. - Favorite plants are stored in a dedicated section for quick access.
10 | As an admin, I want to manage plant listings, so I can ensure all posted plants meet the guidelines. | High | 8 | To Do | - Admins can view, edit, and remove Plant listings. - Admins receive Notifications of new Plant listings for review. - Admins can approve or reject Plant listings.
11 | As an admin, I want to manage user accounts, so I can ensure the platform is used responsibly. | High | 5 | To Do | - Admins can view user profiles and activity. - Admins can suspend or ban Users for violations. - Admins can reset user passwords and manage user privileges.
12 | As an admin, I want to monitor exchanges, so I can track and resolve any issues between users. | Medium | 6 | To Do | - Admins can view exchange transactions. - Admins can intervene and resolve disputes between users. - exchange history is visible and searchable by admin.
13 | As an admin, I want to manage platform-wide announcements, so I can communicate with all users. | Medium | 3 | To Do | - Admins can create and post announcements. - Announcements appear on the user dashboard and notify users. - Admins can set expiration dates for announcements.
14 | As an admin, I want to view analytics of platform activity, so I can make data-driven decisions. | High | 8 | To Do | - Admins can view stats on listings, sales, and user engagement. - Charts and graphs are provided for clear visualization. - Data is updated in real-time.
15 | As an admin, I want to manage disputes, so I can handle complaints between buyers and sellers. | High | 7 | To Do | - Admins receive Notifications of disputes raised by users. - Admins can view detailed complaint logs. - Admins can resolve disputes and provide resolution feedback.
16 | As an admin, I want to manage platform settings, so I can update rules and guidelines for the app. | Medium | 4 | To Do | - Admins can modify platform-wide settings, such as listing fees and category rules. - all Users are notified of rule updates. - Admins can roll back changes if needed.